## Sheet1
VT | [5 empty] | VT Component State Summary | [9 empty] | Libs
Component | Core* | State | Example | LOC | Tests |  |  | All | Core | Non-core | State: Done | State: Done (% of Done) | State: Done Core: Y | State: Done Core: Y (% Done,Core) |  | Component | State | Example | LOC | Tests | Description
Context | Y | Done | No | 120 | No | [10 empty] | meld | Done | No | 213 | No | C-preprocessor meta-library for feature tags and debugging
Registry | Y | Done | No | 721 | No |  | All | 37 | 28 | 9 | 24 | 100% | 18 | 100% |  | detector | Done | No | 193 | No | C++ meta-lib for implementing the detection idiom
Runtime | Y | Done | No | 566 | No | [10 empty] | checkpoint | Done | Partial | 1609 | Done | Checkpointing and serialization library for saving state
Index | Y | Done | No | 416 | Done | State | Done | 24 | 18 | 6 | 24 | 100% | 18 | 100% |  | context | Done | Done | 3389 | Done | Wrapper for boost lightweight context switching via ULTs
Mapping | Y | Done | No | 249 | Done |  | Partially done | 11 | 10 | 1 | N/A | N/A | N/A | N/A
Collective | Y | Partial | No | 146 | No |  | Design | 2 | 0 | 2 | N/A | N/A | N/A | N/A | Total | 4 | 4 | 1 | 5404 | 2
Group | Y | Partial | No | 1465 | No
Barrier | Y | Partial | No | 232 | No | Testing | Fully tested | 5 | 3 | 2 | 5 | 20.83% | 3 | 16.67%
Tree | Y | Partial | No | 76 | No |  | Partially tested | 4 | 3 | 1 | 2 | 8.333% | 2 | 11.11%
Reduce | N | Partial | No | 168 | Partial |  | No tests | 28 | 22 | 6 | 17 | 70.83% | 13 | 72.22%
Termination Detector | Y | Done | No | 640 | No
Event | Y | Done | No | 545 | No | Example | Has example | 0 | 0 | 0 | 0 | 0% | 0 | 0%
Active Messenger | Y | Partial | No | 1557 | Partial |  | No example | 37 | 28 | 9 | 24 | 100% | 18 | 100%
Parameterization | N | Done | No | 206 | No
Pool | Y | Done | No | 310 | Partial | LOC | Lines of code | 19924
RDMA | Y | Done | No | 2937 | No
Scheduler | Y | Done | No | 126 | No
Serialization | Y | Done | No | 471 | Partial
Sequencing | N | Done | No | 2574 | Done
Location | Y | Partial | No | 971 | No
Trace | N | Done | No | 771 | No
Atomic | Y | Done | No | 181 | Done
Concurrent Container | Y | Done | No | 235 | No
Demangle | N | Done | No | 158 | No
Bits | Y | Done | No | 89 | No
Hash | Y | Done | No | 14 | No
Mutex | Y | Done | No | 169 | No
TLS | N | Done | No | 203 | Done
Static checks | N | Done | No | 35 | No
Vrt | Y | Partial | No | 238 | No
Vrt Context | Y | Done | No | 1032 | No
Vrt Context Collection | Y | Partial | No | 1063 | No
Worker | Y | Partial | No | 506 | No
Worker Group | Y | Partial | No | 635 | No
Handler | Y | Done | No | 99 | No
Instrumentation | N | Design | No | 0 | No
Load Balancing | N | Design | No | 0 | No
*Core: A component that is always used if VT is used. Virtualization is considered part of the core VT software stack.

## Sheet2
Libs
| Component | State | Example | LOC | Tests | Description
| meld | Done | No | 213 | No | C-preprocessor meta-library for feature tags and debugging
| detector | Done | No | 193 | No | C++ meta-lib for implementing the detection idiom
| checkpoint | Done | Partial | 1609 | Done | Checkpointing and serialization library for saving state
| context | Done | Done | 3389 | Done | Wrapper for boost lightweight context switching via ULTs
Totals: | 4 | 4 | 1 | 5404 | 2